## project
ITCD 网站切换规划
[14 empty] | Period Highlight: |  |  |  |  | 1 |  |  |  | Plan |  |  | Actual |  |  |  | Postpone
[8 empty] | PLAN |  | PLAN |  | PLAN | PERCENT
任务No. | 优先级 | Dept. | ACTIVITY |  | 责任人 | 前置任务编号 | 任务 | START DATE |  | FINISH DATE |  | DELAY REASON | COMPLETE | PERIODS
[8 empty] | From | Time | To | Time |  |  | Spet | [7 empty] | Oct | [30 empty] | Nov
[14 empty] | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2
1 |  | IT | ITCD的discount 代码上传不正确，要修复 |  | 魏星 |  | 修复测试 | 10,3rd |  | 10,3rd | 12:00pm |  | 100% | bar: Oct 3
2 | 优先 | 业务 | 订单反写和普通抓单注意事项通告 |  | Zoe |  | 邮件开斌T | 9,23rd |  | 9,25th | 12:00pm |  | 100% | bar: Spet 23 to Spet 25
3 |  |  | Order History
4 |  |  |  | PO 号 | 王晓 |  | 添加 | 10,5th |  | 10,7th |  | 未完成 | 0% | bar: Oct 5; Oct 7
5 |  |  |  | 双向链接测试 | Frank |  | 测试 | 10,6th |  | 10,6th |  | 未完成 | 0% | bar: Oct 6
6 |  |  |  | 数量，产品 | 王晓 |  | 迁移 | 10,5th |  | 10,7th |  | 未完成 | 0% | bar: Oct 5; Oct 7
7 |  |  |  | 后台的operator 的调取 | 王晓 |  | 开发 | 10，6th |  | 10,11th |  |  | 0% | bar: Oct 5 to Oct 7; Oct 11
8 |  | IT | Omni 链接 | [9 empty] | 0%
9 |  | IT |  | Island 订单反写到OMNICART的测试 | 余乾开 |  | 测试 | 10,4th |  | 10,10th | 12:00pm | 休假 | 90% | bar: Oct 4 to Oct 10
10 |  | 业务 |  | Island 订单反写到OMNICART的审查 | Zoe |  | 审查 | 10,4th |  | 10,11th | 12:00pm |  | 0% | bar: Oct 4 to Oct 11
11 |  | IT |  | Excel Toner订单反写到OMNICART的开发 | 余乾开 |  | 开发 | 10,4th |  | 10,10th | 12:00pm | 休假 | 100% | bar: Oct 4 to Oct 10
12 |  | 业务 |  | Excel Toner订单反写到OMNICART的审核 | Zoe |  | 审查 | 10,4th |  | 10,11th | 12:00am |  | 0% | bar: Oct 4 to Oct 11
13 |  |  |  | 确认订单到Omniselling | 陈建斌 |  | 测试 | 10,4th |  | 10,10th | 12:00am | 休假 | 0% | bar: Oct 4 to Oct 10
14 |  |  |  | OmniSelling 订单反写 | 陈建斌 |  | 测试 | 10,4th |  | 10,10th | 12:00am | 休假 | 0% | bar: Oct 4 to Oct 10
15 |  |  | Drop shipping 功能修复 |  | 魏星 |  | 休息 | 10,4th |  | 10,11th | 12:00am |  | 70% | bar: Oct 3 to Oct 4; Oct 11
16 |  | IT | 产品数据整理
17 |  |  |  | 产品数据录入 | Zoe,Ming,Ying,CR |  | 上传 | 10.4th |  | 10.13th | 17:00 |  | 80% | bar: Oct 1 to Oct 7; Oct 11 to Oct 13
18 |  | 业务 |  | 产品数据检查 | Zoe |  | 审核 | 10.4th | 6:00pm | 10.13th | 19:00 |  | 0% | bar: Spet 25 to Spet 26; Oct 4 to Oct 7; Oct 11 to Oct 13
19 |  |  |  | 产品价格测试，组别价格，阶梯价格 | Frank |  | 审查 | 10.4th | 9:00am | 10.13th | 5:30pm |  | 90% | bar: Spet 26; Oct 4 to Oct 7; Oct 11 to Oct 13
20 |  | IT |  | 产品价格配置 | Frank |  | 上传 | 10.4th |  | 10.13th | 12:00am | 去仓库，未做 | 0% | bar: Spet 23; Oct 4 to Oct 7; Oct 11 to Oct 13
21 |  |  |  | Related Item | Frank |  | 上传 | 10.4th |  | 10.13th |  | 去仓库，未做 | 0% | bar: Spet 23; Oct 4 to Oct 7; Oct 11 to Oct 13
22 |  |  |  | ITCD产品图片与客户图片的审核 | Frank |  | 上传 | 10.4th | 8:00am | 10.13th |  |  | 30% | bar: Spet 26; Oct 4 to Oct 7; Oct 11 to Oct 13
23 |  |  | 切换域名 |  | 运维 |  | 切换 | 10.13st | 11:00am | 10,14th | 12:00am |  | 0% | bar: Oct 13 to Oct 14
24 |  |  | 域名解析 |  | 向平 |  | 解析 | 10.13st | 12:00pm | 1014th |  |  | 0% | bar: Oct 13 to Oct 14
25 |  | 业务 |  | 网站正式更换信息的同告 | Zoe |  | 通告 | 10.11rd | 11:00am |  |  |  | 0% | bar: Oct 11
26 |  |  | 新网站发布 |  | 魏星， 运维 |  | 发布 | 10.14th |  | 10,14th | 12：00am |  | 0% | bar: Oct 8 to Oct 10; Oct 14
27 |  |  | 新网站测试 |  | 魏星， ZOE, 姚老师 |  |  | 10，15th |  | 10,16th |  |  | 0% | bar: Oct 8 to Oct 16
28 |  | IT | 客户数据的internal credit更新 |  | 魏星 |  | 更新 | 10,15th |  | 10,15th |  | 上线时再做 | 0% | bar: Oct 8 to Oct 10; Oct 15
29 |  |  | pick up 时间设定 为本地时间延后半小时 |  | 魏星 |  | 修复 | 9.23rd |  | 9.24th | 2:00pm |  | 100% | bar: Spet 23 to Spet 24
30 |  |  | 实时抓单 设置为 5 mins |  | 陈建斌 |  | 配置 | 9,26th | 8:00am | 10,10th | 12:00am | 休假 | 0% | bar: Spet 26 to Oct 10
31 |  | 业务 | ITCD后台配置 | bar: Spet 26
32 |  |  |  | 含logo，子账号,发票等 | Ming& Zoe |  | 配置 | 9,23rd |  | 10,14th |  |  | 90% | bar: Spet 23 to Spet 25
33 |  |  |  | 图标，联系方式、付款方式、价格、组别 | [6 empty] | 5:00pm | bar: Spet 23 to Spet 25
34 |  |  |  | 广告语、税务、运输方式、drop-shipping | bar: Spet 23 to Oct 7; Oct 11 to Oct 14
35 |  |  |  | 订单状态优先性 | bar: Spet 23 to Spet 26
36 |  |  |  | Magento授权停止，订单不再进入OS | Zoe |  | 停止 | 9.26th | 6:00pm |  |  |  | 0% | bar: Spet 26 to Oct 7; Oct 11 to Oct 14
37 |  |  |  | ITCD Omnicart授权，对接 | Zoe |  | 授权 | 10,14th | 6:00pm |  |  |  | 0% | bar: Spet 26; Oct 14
38 |  |  |  | 网站准备更换信息的通告 | Zoe |  | 通告 | 10,13th | 11:00am |  |  |  | 0% | bar: Spet 26; Oct 13
39 |  |  |  | 订单信息正确到达仓库的确认 | ming |  | 核实 | 10,11th | 11:00pm | 10,31st | 17:30 |  | 0% | bar: Oct 11 to Oct 31
40 |  |  |  | ITCD Omnicart订单发货正常的确认 | ming |  | 核实 | 10,11th | 11:00pm | 10,31st | 5:30PM |  | 0% | bar: Oct 11 to Oct 31
41 |  |  |  | 订单信息返写到网站 | Zoe |  | 核实 | 10,11th | 11:00pm | 10,31st | 5:30PM |  | 0% | bar: Oct 11 to Oct 31
42 |  |  |  | 后台category 搜索调试 | 魏星 |  | 调试 | 10,12th | 9:00am | 10,12th | 12:00pm |  | 0% | bar: Oct 11 to Oct 31
43 |  | IT |  | ITCD网站的文字信息的审核 | Frank |  | 核对 | 10,6th | 11:00pm | 10,6th | 5:30PM |  | 100% | bar: Oct 6
44 |  |  | magento更换域名，内部使用提前准备, 域名准备周一，magento.itcd.ca |  | 运维 |  | 配置 | 10,2nd | 12:00am |  |  |  | 100% | bar: Oct 2
45 |  |  |  | 订单数据迁移 | 陈建斌 |  | 上传 | 10.1st | 12:00pm | 10.7th | 5:30pm | 休假 | 0% | bar: Oct 2 to Oct 7
46 |  |  |  | b2c&b2b的链接 | 姚老师 |  | 开发 | 9.23rd |  | 待定 |  |  | 0% | bar: Spet 23 to Spet 30; Oct 2 to Oct 10
47 |  |  | 新产品数据生成器 |  | 姚老师 |  | 开发 |  |  | 10,14th |  |  | 0% | bar: Spet 23 to Oct 5; Oct 8 to Oct 14
48 |  |  | 主题设计 |  | 待定 |  | 开发 | 待定 |  |  |  |  | 0%
49 |  |  | B2C网站功能确定 |  | 王晓， 魏星 |  |  | 10，4th |  | 10,4th |  |  | 100% | bar: Oct 4
50 |  |  | 运费设定
51 |  |  |  | 国内运维提供数据 | 陈建斌 |  | 提供 | 10,8th |  | 10,9th |  | 休假 | 0% | bar: Oct 8 to Oct 10
52 |  |  |  | 手动调整运费功能 | 姚老师 |  | 开发 |  |  | 10,11th |  |  | 0% | bar: Spet 23 to Oct 5; Oct 8 to Oct 10
53 |  |  |  | 做运费数据表格 | Zoe |  | 开发 | 10,11th |  | 10,15th |  |  | 0% | bar: Oct 8 to Oct 15
54 |  |  | 网站平行运行 | bar: Oct 8 to Oct 15
55 |  |  |  | 每日数据备份 | 运维 |  | 测试 | 10,1st |  | 10,14th |  |  | 0% | bar: Oct 2 to Oct 14
56 |  |  |  | 平行网站下单 | Zoe Ming |  |  | 10,1st |  | 10,14th |  |  | 0% | bar: Oct 2 to Oct 14
57 |  |  |  | 订单测试进入Omniselling | 陈建斌 |  |  | 10,1st |  | 10,14th |  | 休假 | 0% | bar: Oct 2 to Oct 14
58 |  |  | 优化财务功能 | bar: Oct 7 to Oct 10
59 |  |  |  | 财务报表 | 王晓 |  | 优化 | 10,7th |  | 10,20th |  |  | 0% | bar: Oct 7 to Oct 10
60 |  |  |  | 销售报表功能 | 王晓 |  | 开发 |  |  | 10,11th |  |  | 85% | bar: Oct 11
61 |  |  |  | Inovice MGMT 优化 | 王晓 |  | 优化 | 10,7th |  | 10,20th |  |  | 0% | bar: Oct 8 to Oct 10
62 |  |  | 前段订单的internal credit BUG |  | 王晓 |  | 修复 | 10,6th |  | 10,11th |  |  | 0% | bar: Oct 8 to Oct 10