## project
ITCD 网站切换规划
[12 empty] | Period Highlight: |  |  |  |  | 1 |  |  |  | Plan |  |  | Actual
[6 empty] | PLAN |  | PLAN |  | PLAN | PERCENT
任务No. | Dept. | ACTIVITY | 责任人 | 前置任务编号 | 任务 | START DATE |  | FINISH DATE |  | DELAY REASON | COMPLETE | PERIODS
[6 empty] | From | Time | To | Time |  |  | Spet | [7 empty] | Oct
[12 empty] | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7
1 | IT | ITCD的discount 代码上传不正确，要修复 | Frank & 王晓 |  | 修复测试 | 9,23rd |  | 9,25th | 12:00pm | bar: Spet 23 to Spet 25
2 | 业务 | 订单反写和普通抓单注意事项通告 | Zoe |  | 邮件开斌T | 9,23rd |  | 9,25th | 12:00pm |  | 100% | bar: Spet 23 to Spet 25
3 | IT | Island 订单反写到OMNICART的测试 | 余乾开 |  | 测试 | 9,23rd |  | 9,25th | 12:00pm | 南沙搬迁,测试环境的cassandra数据库目前运维同事还未搭建起来,暂时没有测试环境可用 | bar: Spet 23 to Spet 25
4 | 业务 | Island 订单反写到OMNICART的审查 | Zoe |  | 审查 | 9,25th | 1:00pm | 9.26th | 12:00am | bar: Spet 25 to Spet 26
5 | IT | Excel Toner订单反写到OMNICART的开发 | 余乾开 |  | 开发 | 9,23th |  | 9,25th | bar: Spet 23 to Spet 25
6 | 业务 | Excel Toner订单反写到OMNICART的审核 | Zoe |  | 审查 | 9,25th | 1:00pm | 9.26th | 12:00am | bar: Spet 25 to Spet 26
7 | IT | 客户数据的internal credit更新 | 魏星 |  | 更新 | 9,26th | 5:30pm | bar: Spet 26
8 | IT | 产品数据录入 | 王晓 |  | 上传 | 9.23rd |  | 9.25th | 17:00 | bar: Spet 23 to Spet 25
9 | 业务 | 产品数据检查 | Zoe |  | 审核 | 9,25rd | 6:00pm | 9.26th | 19:00 | bar: Spet 25 to Spet 26
10 | IT | 复制INKESALE.CA上正式产品图片到ITCD | 运维 |  | 上传 | 9,26th | 8:00am | bar: Spet 26
11 |  | pick up 时间设定 为本地时间延后半小时 | 魏星 |  | 开发 | 9.23rd |  | 9.24th | 2:00pm | bar: Spet 23 to Spet 24
12 |  | 实时抓单 设置为 5 mins | 陈建斌 |  | 配置 | 9,26th | 8:00am | bar: Spet 26
13 | 业务 | ITCD后台配置，含logo，子账号,发票等 | Ming& Zoe |  | 配置 | 9,23rd |  | 9,25th | bar: Spet 23 to Spet 25
|  | 图标，联系方式、付款方式、价格、组别 | [6 empty] | 5:00pm | bar: Spet 23 to Spet 25
广告语、税务、运输方式、drop-shipping | bar: Spet 23 to Spet 25
订单状态优先性 | bar: Spet 23 to Spet 25
14 | IT | 产品价格配置 | Frank |  | 上传 | 9,23rd |  | 9.25th | 12:00am | bar: Spet 23
15 | 业务 | 产品价格测试，组别价格，阶梯价格 | Zoe,Lucy,Ying |  | 审查 | 9.26th | 9:00am | 9.26th | 5:30pm | bar: Spet 26
16 |  | Magento授权停止，订单不再进入OS | Zoe |  | 停止 | 9.26th | 6:00pm | bar: Spet 26
17 |  | ITCD Omnicart授权，对接 | Zoe |  | 授权 | 9.26th | 6:00pm | bar: Spet 26
18 |  | 网站准备更换信息的通告 | Zoe |  | 通告 | 9.26th | 11:00am | bar: Spet 26
19 |  | 订单信息正确到达仓库的确认 | ming |  | 核实 | 9.26th | 11:00pm | 10,1st | 17:30 | bar: Spet 26 to Oct 1
20 |  | ITCD Omnicart订单发货正常的确认 | ming |  | 核实 | 9.26th | 11:00pm | 10,1st | 5:30PM | bar: Spet 26 to Oct 1
21 |  | 订单信息返写到网站 | Zoe |  | 核实 | 9.26th | 11:00pm | 10,1st | 5:30PM | bar: Spet 26 to Oct 1
22 | IT | ITCD网站的文字信息的核对 | Frank |  | 核对 | 9.26th |  | 10,1st | 5:30PM | bar: Spet 26 to Oct 1
23 |  | 切换域名 | 运维 |  | 切换 | 10.1st | 11:00am | bar: Oct 1
24 |  | 域名解析 | 向平 |  | 解析 | 10.1st | 12:00pm | bar: Oct 1
25 |  | magento更换域名，内部使用提前准备, 域名准备周一，magento.itcd.ca | 运维 |  | 配置 | 10,2nd | 12:00am | bar: Oct 2
26 | 业务 | 网站正式更换信息的同告 | Zoe |  | 通告 | 10.1st | 11:00am | bar: Oct 1
27 | IT | 订单数据迁移（哪些数据） | 魏星 |  | 上传 | 10.1st | 12:00pm | 10.7th | 5:30pm | bar: Oct 1 to Oct 7
28 | IT | b2c&b2b的链接 | 姚老师 |  | 开发 | 9.23rd
29 | IT | 销售报表功能 | 待定 |  | 开发 | 待定 | bar: Oct 1
30 | IT | 新产品数据生成器 | 待定 |  | 开发 | 待定 | bar: Oct 1